## Slide 1
CS 301R · SOFTWARE ENGINEERING STUDIO I
From Design to Work
Session 17 — epics, milestones, issues, and a board
Monday, November 2, 2026
Notes: Phase 4 begins: the build. Before class: open Prop Loft's issues, the epic 'Find an item', the milestones page, and the project board in tabs, plus the search issue showing its request and its Triaged note. Have the Setting Up Your Board page up; it's the step-by-step students follow in the workshop. Laptops required. CP8 is due end of day Wednesday, Nov 4; today produces most of it.

## Slide 2
TODAY
Turn your design into work someone can pick up
The tracker is the project's memory
5 min
The decomposition ladder: MVP → epics → issues
14 min
Milestones and the honest calendar
10 min
The board, labels, and pathways in
10 min
Workshop: decompose your own MVP
28 min
Wednesday: estimate, sequence, commit
8 min
CS 301R · Session 17 · From Design to Work
2
Notes: Thirty seconds. The first forty minutes are short teaching blocks, every one shown on Prop Loft. The highlighted row is the point of the day: 28 minutes building your own tracker, live, with me circulating. Anything you build today counts toward CP8, due Wednesday. Keep the teaching blocks moving; the workshop time is the part to protect.

## Slide 3
THE TRACKER IS THE PROJECT'S MEMORY
Documents become software here
Weeks 1–8
Documents: the proposal, the design
→
The tracker
Where the design becomes work
→
Weeks 9–13
Working software, a piece at a time
WHO READS IT
You, and anyone you build with
What's next, and who's on it. Solo, it's how you remember.
Anyone checking on progress
What you said you'd do, and what you did. (Here: the Week-11 audit.)
A future contributor
Where the project is going, and where there's room to help.
Unwritten work doesn't get done. Vaguely written work gets done wrong.
CS 301R · Session 17 · From Design to Work
3
Notes: Five minutes. The shift: until now you've produced documents; from here you produce software, and the tracker is where one turns into the other. One click per reader. The first is obvious. The second is anyone checking on progress: a manager, a sponsor, and in this course the Week-11 auditor. The third is the founder's reason: a plan in public is how a stranger sees there's a future. Fourth click, say it plainly.

## Slide 4
WHAT A TRACKER HAS TO DO
Five jobs, and a good default for each
THE JOB
THE DEFAULT
Describe each piece of work
What exactly needs doing?
A task form with acceptance criteria
Notice what's new
What hasn't anyone read?
A needs triage label
Group work by the value it delivers
What does this add up to?
Epics: parent issues + sub-issues
Group work by when it's due
What has to be true by when?
Milestones
Show each item's state
What's happening right now?
A public project board
Defaults, not rules. Change any of them; write what you do instead, and why, in CONTRIBUTING. Keep a review state: every project works through PRs.
CS 301R · Session 17 · From Design to Work
4
Notes: Two minutes; this is the map for the rest of the day. Every tracker, on any tool, has to do these five jobs. The right column is what we'll set up, and what Prop Loft uses. Click: these are defaults, the same rule as your git policies in Session 13. Most of you will take them, and that's fine. Change one if your project works differently, and say why in CONTRIBUTING. The only fixed piece is a review state.

## Slide 5
THE DECOMPOSITION LADDER
MVP → epics → issues, on Prop Loft
MVP
What the design commits to
One theater's costume stock: find it, check it out, add it, from a phone
Epic
A slice of user-visible value · 3–5 per MVP
Check out and return
Issue
One coherent, reviewable change · usually one PR
Enforce one open checkout per item
Read epics off the design's goals, not its components. "Check out and return" touches the web UI, checkout, and auth. That's normal.
CS 301R · Session 17 · From Design to Work
5
Notes: Two minutes. One click per rung, top down. The MVP is the design doc's commitment. An epic is something a user gets, and Prop Loft has five. An issue is one change a reviewer can review as a unit, usually one pull request. Fourth click is the common mistake: epics named after layers of the code. 'Backend' isn't something a volunteer gets. Epics cut across components, and that's fine.

## Slide 6
PROP LOFT'S EPICS
Five, each named for what a volunteer gets
E1
Find an item
"Do we own this?" from a phone, in under a minute
E2
Check out and return
Who has it, for which show, due back when
E3
Add an item
With a photo, and no one showing you how
E4
Roles and phone layout
What a volunteer may do; pages that work on a phone
E5
Run it at the theater
Its own server, and a real strike night
Each traces to a goal in the design. If an epic doesn't, either the design is missing a goal or the epic is missing a reason.
CS 301R · Session 17 · From Design to Work
6
Notes: One minute. Read the five aloud and ask which goal in Prop Loft's design each comes from: E1 is goal 1, E2 goal 2, E3 goal 3, E4 and E5 goal 4, running without a developer. The bottom line is the check students run on their own: trace every epic to a goal. Mention that E4 and E5 aren't broken down yet, on purpose; they're on the roadmap, and we'll see why in ten minutes.

## Slide 7
AN EPIC ON GITHUB
A parent issue, with the work hung under it
Epic: Find an item
epic
Sub-issues · 2 of 4
Search items by name
Show an item's detail page
Filter items by category and size
Say so when a search finds nothing
1
Label it epic
Add the label; explain it in CONTRIBUTING
2
Write it like a task
Done when the slice works and every sub-issue is closed
3
Hang the work under it
Create sub-issue, or Add existing issue
Also works: an Epic issue type, or one milestone per epic. Keep the sub-issues either way: they give the epic its progress bar.
CS 301R · Session 17 · From Design to Work
7
Notes: Two minutes; switch to the Prop Loft tab if you can. The left is what an epic looks like a week into the build: a parent issue whose sub-issues are the work, with a progress bar that moves as they close. The three steps are the default. Create sub-issue sits at the bottom of the description, not the comments; people miss it. The italic line is the alternatives: an issue type, or a milestone per epic when each epic is also a release.

## Slide 8
TWO KINDS OF ISSUES
Same tracker, different jobs
Requests
Session 15's anatomy
Written by
anyone: a user, a stranger
Says
what's wrong, or what's needed
Shape
steps, expected vs. actual; or the problem, who has it, the workaround
Work items
Today
Written by
a maintainer, while planning
Says
what will be built, and how you'll know it's done
Shape
a goal, context, and acceptance criteria
Triage turns a request into a work item: read it, decide, and add what's missing.
CS 301R · Session 17 · From Design to Work
8
Notes: Two minutes. This answers the question you'll have: the issue forms you built for CP7 don't ask for acceptance criteria, and they shouldn't. They're for requests from anyone, and a request is the problem as the reporter sees it. A work item is the maintainer's decision about what to build. Both live in the same tracker. Click: triage is the bridge, and the next slide is one, on Prop Loft.

## Slide 9
TRIAGE, ON PROP LOFT
The request stays on top. The decision goes below.
As filed, through the feature form
Search items by name, category,
and size
The problem
A volunteer needs to know whether we
own something, from a phone.
Who has this problem
Wardrobe volunteers, on the shop floor
Added by the maintainer
Retitled: Search items by name
Goal A volunteer finds an item by
typing part of its name.
Context Design §2 goal 1 · part of E1
[ ] The list filters by name, any case
[ ] An empty search shows everything
[ ] Tests: a match, case, empty search
Triage also split it. Filtering by category and size became its own task, in the second milestone. Now each one is a single pull request, and the first can ship for the demo.
CS 301R · Session 17 · From Design to Work
9
Notes: Two minutes; open the real issue if you can, since it shows both halves. Left: the request as a stranger filed it, through the feature form. Click: what the maintainer added below it, without editing the request away. Read the acceptance criteria aloud; each is true or false when the PR is ready. Second click: triage doesn't just accept, it can split. One request became two tasks in two milestones.

## Slide 10
DESCRIBING PLANNED WORK
Four fields make an issue ready to work
Goal
One sentence: what's true for a user when it's done.
Context
Links, not a retelling: the design section, the epic, the request it answers.
Acceptance criteria
"Checkout works" is a hope. "An item that's already out can't be checked out again" is a criterion.
Where to start (optional)
For a newcomer: the file, the function to imitate, the test to copy.
Default: a task form, .github/ISSUE_TEMPLATE/task.yml (copy Prop Loft's). Also works: a Markdown template, GitHub's Task issue type, or a reviewer who insists on criteria.
CS 301R · Session 17 · From Design to Work
10
Notes: Ninety seconds. The highlighted field is the one that matters most: acceptance criteria are how a reviewer, or the demo, can say 'done' without arguing. A form makes this shape the easy path, the same way the bug form did for reports; it goes in through a PR like any other change. The alternatives are real, and some of you may prefer one. Whatever you pick, the four fields are the point.

## Slide 11
HOW BIG IS AN ISSUE?
The shape of the work, not the clock
One coherent change?
Can one person carry it?
Reviewable as a unit?
Shows progress before it's done?
Weeks can be fine. A migration or a hard concurrency bug is one thing; split it and the pieces mean nothing. Show progress: a draft PR, a checklist.
Split when you can. If it breaks into pieces that are each useful and reviewable alone, it's an epic wearing an issue's costume.
In this course: most land in a few focused hours to a couple of days. A two-week issue is 40% of the build with no checkpoint.
CS 301R · Session 17 · From Design to Work
11
Notes: Two minutes. The four tests are about the work, not time. First click: on real projects, issues that take weeks exist and are fine when the work is one indivisible thing; what they owe everyone is visible progress. Second click: the real rule, split when the pieces stand alone. Third: the course-scale version. With about five build weeks, a two-week issue is a big bet with no checkpoint. Bigger is allowed; say so in the issue.

## Slide 12
QUICK CHECK
Which of these is ready to work?
Implement the frontend
An epic in disguise: it splits into useful pieces
Enforce one open checkout per item
Ready: one change, one pull request
Investigate why checkouts double-post on slow networks
Ready, even at a week: it's one thing
Checkout
A mystery: no goal, no criteria
Use crispy-forms for the checkout form
Stale by design: the design doc owns that
CS 301R · Session 17 · From Design to Work
12
Notes: Three minutes. Hands up or call-outs for each before you click. The third is the one people get wrong: it takes a week, and it's still one issue, because there's no useful half of an investigation. The last two are the other anti-patterns: a title with nothing behind it, and an issue that dictates implementation the design doc already decided. That one goes stale the moment the design changes.

## Slide 13
MILESTONES
Epics are what. Milestones are when. They cut across.
M1 · Demo-able core
M2 · MVP complete
Roadmap
E1 Find an item
Search · item page
Filters · empty search
E2 Check out, return
Record · check out · who has it
Returns · overdue list
E3 Add an item
Add form · photo · iPhone test
E4 Roles, layout
Roles · phone layout
E5 Run it there
Setup guide
Deploy · 60 items · strike night
Prop Loft. M1 takes a slice of three epics; nothing in E4 is due this term.
CS 301R · Session 17 · From Design to Work
13
Notes: Two minutes. Read across a row: an epic spreads over time. Read down a column: a milestone takes slices of several epics. M1 is the thinnest path through E1, E2, and E5 that a volunteer could actually use. On GitHub, a milestone is Issues, Milestones, New: a title that says what it delivers, a due date, and a line on what's true when it closes. Each issue goes in one milestone.

## Slide 14
THE HONEST CALENDAR
Count the hours, then cut
Today
Mon, Nov 2
M1 · progress demo
Wed, Nov 18 (CP10)
M2 · launch package
Wed, Dec 2 (CP11)
Capacity per milestone
maintainers × ~7 outside hours × 2 weeks, minus review
Solo: 1 × 7 × 2 = 14 hours, about 12 after review
Add up the issues. If they don't fit, cut until they do, and write down what moved.
Detail M1 fully, M2 loosely. Plans sharpen as you get closer; detailed issues for work a month out mostly get rewritten.
CS 301R · Session 17 · From Design to Work
14
Notes: Two minutes. Two fixed dates, so two milestones of about two weeks each. First click: the arithmetic from Session 8, now with real numbers. Seven is the outside hours a week the ten-hour course load leaves after class; on a team, multiply. Second click: count, then cut. A milestone that fits and closes on time beats an impressive one that slips. Wednesday you'll size every M1 issue against this number.

## Slide 15
PROP LOFT'S CUT
The design planned five slices. The calendar holds two.
Slice 1
Find, open, check out, see it marked out
M1
Slice 2
Returns and the overdue list
M2
Slice 3
Add an item, with a photo
M2
Slice 4
Roles and phone layout
Roadmap
Slice 5
Deploy, 60 items, strike night
Roadmap
docs/roadmap.md says so, out loud. What was cut, why, and where a contributor could pick it up. A roadmap isn't where cut work goes to die; it's where the next person finds room.
CS 301R · Session 17 · From Design to Work
15
Notes: Ninety seconds. Prop Loft's design plans five vertical slices before its real-world trial. Counting one maintainer's hours, two milestones hold three slices. Click: four and five move to the roadmap. Second click: the cut is written down in docs/roadmap.md, with reasons, framed as places to help. That's CP8's roadmap criterion, and it's 20% of the grade. Open the file if you have time.

## Slide 16
NOTICING WHAT'S NEW
How do you know what's still waiting?
A label the forms apply
Removed when a maintainer has read it. Prop Loft's: needs triage.
A New column
Auto-add drops new issues there; the column is the queue.
No labels = untriaged
Zero setup. Breaks once forms add labels.
A person and a day
Someone reads everything new, every week.
Using a label? Create it before a form names it. A form skips labels that don't exist, without a warning. File a test issue to check.
CS 301R · Session 17 · From Design to Work
16
Notes: Two minutes. Callback to Session 16: your communication norms promised a response time, and CP7 asked how you'd know what's waiting. This is that answer, now called triage. The highlighted card is the default; the others are real alternatives. The amber warning is the trap: the forms silently drop a label that doesn't exist yet. Ask who has already filed a test issue through their own form.

## Slide 17
THE BOARD
Columns are the states your work actually passes through
Backlog
Check an item out from its page
Record a return
Ready
Show an item's detail page
Record checkouts
In progress
Search items by name
In review
Your review policy lives here
Done
Fills itself: closed issues and merged PRs move here
Default columns. Change them to fit how your project works, but keep a review state. Ready means acceptance criteria are written.
CS 301R · Session 17 · From Design to Work
17
Notes: Ninety seconds. This is Prop Loft's board at the start of the build. Walk the columns: Backlog is decided, Ready means anyone could pick it up because the criteria are written, In progress means someone said they're on it. In review is where a PR waits; it's the column that shows whether your review policy is real. Done fills itself. Click for the default rule. A board where everything is In progress tells a reader nothing.

## Slide 18
SETTING IT UP · LIVE
Five steps, at your organization
1
Create it
Org → Projects → New project → Board. Check Import items from repository.
2
Set the columns
They're the Status field's options. Edit them from any column's ⋯ menu.
3
Set up the workflows
Workflows: auto-add is:issue is:open; new items → Backlog; closed and merged → Done.
4
Make it public, then link it
A new project is private, even in a public org. Then repo → Projects → Link a project.
5
Add two views
Swimlanes by milestone (what's left?) and by parent issue (how's each epic?). Save each.
Every step, with screenshots: Canvas → Course Resources → Setting Up Your Board.
CS 301R · Session 17 · From Design to Work
18
Notes: Demo it live on Prop Loft or a scratch org, about four minutes, then leave this up during the workshop. Step 1 imports existing issues because auto-add only catches new ones, and free organizations get one auto-add workflow. Step 3: the board holds issues only; a PR shows on the card of the issue it closes. Which workflows start out on varies, so check each one. Step 5: on a board the setting is called Swimlanes, and an unsaved view shows a dot on its tab and reverts. Step 4 is the trap: projects start private, so a stranger or the auditor sees nothing. Say it twice. The page has every click; students don't need to copy this down.

## Slide 19
A WAY IN FOR A NEWCOMER
Two or three real starting points
Prop Loft · a good first issue
Show an item's detail page
good first issue
Where to start
- A view beside item_list in
catalog/views.py (get_object_or_404)
- Its URL; a template next to the list's
- A test modeled on ItemListTests,
plus one for a missing item (404)
Small, and needs no history
A newcomer shouldn't need to know why things are the way they are.
Says where to start
The file, the function to imitate, the test to copy. Two extra sentences.
Findable from the front door
README and CONTRIBUTING link the board and the roadmap.
A good first issue with no context is a trap, not an invitation.
CS 301R · Session 17 · From Design to Work
19
Notes: Ninety seconds. Prop Loft's item-detail issue is the model: a newcomer knows which file to open and what to copy before they've read anything else. good first issue is GitHub's own label for this, so there's rarely a reason to change it. Contribution pathways are 20% of CP8 and they're tested again at launch. Tag two or three in the workshop, and write their Where to start sections, not just the label.

## Slide 20
TWO LAYERS OF "DONE"
This change, and every change
Acceptance criteria
In each issue: what this change must do
The list filters by name, ignoring case
An empty search shows everything
Tests cover a match, case, and empty
Definition of done
In the git standards: what every change must pass
Reviewed under the project's rules
Merged; tests pass on main
Docs say what the code now does
Its issue closed, with a note if it differs
You wrote one in CP6. Revisit it now there's code: does it name your test command? Keep it in that one place and link it; don't copy it into issues.
CS 301R · Session 17 · From Design to Work
20
Notes: Ninety seconds. Left: acceptance criteria belong to one issue. Right: Prop Loft's definition of done, which every change passes regardless of what it is. Students already wrote one in their git standards for CP6. Click: CP8 grades the revised version, so the question is whether a reviewer could check each item now that there's code. It stays in the git standards; a copy elsewhere drifts.

## Slide 21
WORKSHOP · 28 MIN
Decompose your own MVP, live in your tracker
5 min
Set up
Create the project (public, linked); add the epic label and a task form, or your alternative with its reason
6 min
Epics
3–5 parent issues, named for value, each linked to a goal in your design
12 min
M1, in full
Sub-issues with real acceptance criteria; triage your CP7 seed issues; owners on the first few
5 min
Dates and pathways
M1 and M2 dated; issues placed and given a status; 2–3 good first issues with Where to start
I'll ask: Which issue is secretly an epic? · What must be true on Nov 18, and is that M1? · What did you change from the defaults, and why?
CS 301R · Session 17 · From Design to Work
21
Notes: Keep time out loud at each step. Most students are solo, so circulate to every repo at least twice. Push epics first: projects that start writing issues before epics end up with a flat pile. In the M1 block, read acceptance criteria aloud back to their authors and ask if a reviewer could mark each true or false. Whatever isn't finished, M2 especially, is homework: M2 only needs to be coarse by Wednesday.

## Slide 22
The tracker is your project's public memory, and its welcome mat.
BEFORE WEDNESDAY, NOV 4
Finish M1's issues; break M2 down coarsely, at the epic or rough-issue level
Write docs/roadmap.md, and revisit the definition of done in your git standards
Wednesday: size every M1 issue, find the dependencies, and commit to the vertical slice
CP8 Project Plan & Roadmap is due end of day Wednesday, Nov 4. Submit your public board's URL.
CS 301R · Session 17 · From Design to Work
22
Notes: Close in a few minutes. Say the one-liner. M1 fine-grained and M2 coarse is the right shape, not a shortcut. The roadmap and the definition of done are files, so they go in through PRs. Wednesday is estimation and sequencing, and the slice statement on M1 becomes the progress-demo commitment. Remind them to check that the board is public before submitting: a private board can't be graded.